## Aneesh House
Aneesh Thodupuzha Bill 5
S.No | Description | Nos | Length | Breadth | Depth | Qty | Remarks
Main Building
1 | Providing and laying PCC 1:4:8
| servese yard | 1 | 5.3 | 3.2 | 0.15 | 2.544
|  | 1 | 5.3 | 0.5 | 0.15 | 0.3975
| servent toilet | 1 | 1 | 2 | 0.45 | 0.9
| master balcony step | 1 | 5.58 | 0.6 | 0.1 | 0.3348
[6 empty] | 4.1763 | Cu.m
2 | Providing and laying RCC M 20 Using 20 mm metal for columns,lintals,walls
| bridge | 1 | 2.2 | 3 | 0.12 | 0.792
| main entrence | 3 | 1.55 | 0.55 | 0.1 | 0.25575
| work area slab | 2 | 4.45 | 0.8 | 0.15 | 1.068
| beam | 1 | 23.4 | 0.2 | 0.4 | 1.872
[6 empty] | 3.9878 | Cu.m
3 | Providing and constructing Brick masonary
|  | 4 | 0.8 | 0.1 | 0.7 | 0.224
|  | 3 | 1.2 | 0.1 | 1.2 | 0.432
| master balcony step | 1 | 5.58 | 0.6 | 0.15 | 0.5022
|  | 1 | 5.58 | 0.3 | 0.15 | 0.2511
[6 empty] | 1.4093 | Cu.m
4 | Prepare the surfaces and plaster in cm 1:4
| formal living | 2 | 1.43 | 0.15 |  | 0.429
|  | 2 | 1.3 | 0.15 |  | 0.39
|  | 2 | 2.5 | 0.1 |  | 0.5
|  | 2 | 1.3 | 0.1 |  | 0.26
|  | 1 | 1.2 | 0.1 |  | 0.12
|  | 1 | 5.36 | 5.36 |  | 28.7296
| family room | 1 | 5.66 | 1.27 |  | 7.1882
|  | 1 | 2.5 | 0.1 |  | 0.25
|  | 1 | 5.66 | 1.2 |  | 6.792
|  | 1 | 2 | 0.45 |  | 0.9
|  | 1 | 0.9 | 0.25 |  | 0.225
| son bed | 1 | 4.5 | 2.38 |  | 10.71
|  | 1 | 2.5 | 0.1 |  | 0.25
|  | 1 | 5.6 | 2.62 |  | 14.672
|  | 1 | 2.7 | 2.5 |  | 6.75
|  | 1 | 0.9 | 0.23 |  | 0.207
| library | 1 | 4.15 | 2.1 |  | 8.715
[6 empty] | 87.0878 | Sq.m
5 | Wooden floor works
| master bed | 1 | 6 | 4.82 |  | 28.92
|  | 1 | 2.9 | 0.1 |  | 0.29
|  | 1 | 0.9 | 0.25 |  | 0.225
|  | 1 | 2.35 | 2.86 |  | 6.721
| girl bed | 1 | 5.8 | 4.14 |  | 24.012
|  | 1 | 0.9 | 0.2 |  | 0.18
|  | 2 | 0.9 | 0.25 |  | 0.45
|  | 1 | 2.25 | 3.95 |  | 8.8875
| mother bed | 1 | 5.7 | 4.14 |  | 23.598
|  | 1 | 0.9 | 0.4 |  | 0.36
|  | 1 | 0.9 | 0.25 |  | 0.225
|  | 1 | 1.8 | 3.95 |  | 7.11
|  | 1 | 0.9 | 0.65 |  | 0.585
| formal dining | 1 | 7.13 | 4.5 |  | 32.085
|  | 1 | 1.2 | 0.08 |  | 0.096
|  | 1 | 2.18 | 0.35 |  | 0.763
|  | 1 | 0.9 | 0.45 |  | 0.405
| guest bed | 1 | 4.6 | 3.6 |  | 16.56
|  | 1 | 1 | 0.55 |  | 0.55
|  | 1 | 2.29 | 1.3 |  | 2.977
|  | 1 | 1 | 0.08 |  | 0.08
|  | 1 | 0.9 | 0.1 |  | 0.09
|  | 1 | 1.7 | 0.1 |  | 0.17
|  | 1 | 4.78 | 1.2 |  | 5.736
[6 empty] | 161.0755 | Sq.m
6 | Providing wooden ceiling works
|  | 1 | 5.4 | 2 |  | 10.8
|  | 1 | 1.8 | 0.4 |  | 0.72
[6 empty] | 11.52 | Sq.m
7 | Wodden covering works for steel columns and beams
| master balcony | 1 | 1.8 |  |  | 1.8
|  | 1 | 5.4 |  |  | 5.4
|  | 1 | 2 |  |  | 2
|  | 1 | 5.6 |  |  | 5.6
|  | 1 | 1.7 |  |  | 1.7
|  | 1 | 1.67 |  |  | 1.67
|  | 1 | 1.67 |  |  | 1.67
|  | 1 | 1.8 |  |  | 1.8
|  | 8 | 1.72 |  |  | 13.76
|  | 2 | 1.42 |  |  | 2.84
|  | 2 | 1.62 |  |  | 3.24
| son bed balcony | 1 | 2.94 |  |  | 2.94
|  | 1 | 3.34 |  |  | 3.34
|  | 6 | 1.72 |  |  | 10.32
| nadapandal | 2 | 12.92 |  |  | 25.84
|  | 5 | 2.37 |  |  | 11.85
|  | 10 | 1.72 |  |  | 17.2
| front varandah | 1 | 3.38 |  |  | 3.38
|  | 1 | 3.58 |  |  | 3.58
|  | 1 | 13.7 |  |  | 13.7
|  | 1 | 14.1 |  |  | 14.1
|  | 1 | 7.3 |  |  | 7.3
|  | 1 | 7.5 |  |  | 7.5
|  | 4 | 1.67 |  |  | 6.68
|  | 7 | 1.8 |  |  | 12.6
|  | 2 | 1.6 |  |  | 3.2
|  | 26 | 1.72 |  |  | 44.72
|  | 4 | 3.1 |  |  | 12.4
|  | 2 | 3.1 |  |  | 6.2
|  | 2 | 1.72 |  |  | 3.44
|  | 4 | 5.65 |  |  | 22.6
|  | 4 | 5.95 |  |  | 23.8
|  | 4 | 5.6 |  |  | 22.4
|  | 8 | 1.72 |  |  | 13.76
|  | 4 | 0.9 |  |  | 3.6
| formal dining | 9 | 4.48 |  |  | 40.32
| main entrence | 2 | 2 |  |  | 4
|  | 2 | 5.48 |  |  | 10.96
| family room | 2 | 10.86 |  |  | 21.72
|  | 2 | 2.85 |  |  | 5.7
[6 empty] | 420.63 | RM
8 | Additional labour charges for various works
| Skirting works carpenter | 40 | 950 |  |  | 38000
| toilet pergola carpenter | 9 | 950 |  |  | 8550
| varandah percola carpenter | 18 | 950 |  |  | 17100
| guest bed | 5 | 950 |  |  | 4750
| service yard | 1 | 950 |  |  | 950
| gate door | 14 | 950 |  |  | 13300
| sliding and folding door work | 30 | 950 |  |  | 28500
| patch plastering | 29 | 1300 |  |  | 37700
|  | 29 | 1000 |  |  | 29000
| basement earth filling | 12 | 800 |  |  | 9600
| basement cleaning | 6 | 800 |  |  | 4800
| courtyard earth filling | 24 | 800 |  |  | 19200
| roof top cleaning | 7 | 800 |  |  | 5600
| heat pump area work | 6 | 800 |  |  | 4800
| work area | 2 | 800 |  |  | 1600
| granite area patch plastering | 6 | 1300 |  |  | 7800
|  | 3 | 1000 |  |  | 3000
| metal filling | 11 | 800 |  |  | 8800
| earth filling planter boxes | 12 | 800 |  |  | 9600
| pond area rubble work | 2 | 1100 |  |  | 2200
| cleaning house | 39 | 800 |  |  | 31200
| Welding works from 1/8/21 to 16/10/21 |  |  |  |  | 196750
| Electrical wages from 1/4/21 to 16/10/21 |  |  |  |  | 189600
| Total |  |  |  |  | 672400
| Add oh and cp 10% |  |  |  |  | 67240
| Total |  |  |  |  | 739640
Say Rs 7,39,600/-

## abst -H
Abstract Aneesh House - RAB 5
S.No. | Description | Unit | Qty | Rate | Amount
1 | Providing and laying PCC 1:4:8 | Cu.m | 4.18 | 2650 | 11077
2 | Providing and laying RCC M 20 for all concreting | Cu.m | 3.99 | 10950 | 43690.5
3 | Providing and constructing brick masonary | Cu.m | 1.41 | 6500 | 9165
4 | Prepare the surfaces and plaster in cm 1:4 | Sq.m | 87.09 | 350 | 30481.5
5 | Providing wooden flooring | Sq.m | 161.08 | 4790 | 771573.2
6 | Providing wooden ceiling | Sq.m | 11.52 | 4790 | 55180.8
7 | Wooden covering for steel columns and beams as per design | RM | 420.63 | 250 | 105157.5
8 | Additional labour charges |  |  |  | 739600
| Total |  |  |  | 1765925.5

## abtst - C
Abstract Crusher - RAB 5
S.No. | Description | Unit | Qty | Rate | Amount
Dam works
| Providing and laying PCC 1:4:8 | Cu.m | 13.23 | 2650 | 35059.5
| Providing RCC M20 for footing | Cu.m | 32.96 | 4000 | 131840
| Providing RCC M20 for Walls | Cu.m | 77.2 | 10950
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 17200 | 15 | 258000
Drain works
| Providing RCC M20 for footing | Cu.m | 51.93 | 4000 | 207720
| Providing RCC M20 for Walls | Cu.m | 35.97 | 10950 | 393871.5
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 3700 | 15 | 55500
Work shop
| Providing and laying PCC 1:4:8 | Cu.m | 5.81 | 2650 | 15396.5
| Providing and constructing solid block walls | Cu.m | 2.31 | 5500 | 12705
Canteen area
| Providing and laying PCC 1:4:8 | Cu.m | 0.9 | 2650 | 2385
| Providing and constructing solid block walls | Cu.m | 1.25 | 5500 | 6875
| Prepare the surfaces and plaster in cm 1:4 | Sq.m | 36.85 | 325 | 11976.25
Qurry road works
| Providing and laying PCC 1:4:8 ( using Ajax) | Cu.m | 24.9 | 1750 | 43575
| Providing and constructing solid block walls | Cu.m | 4.44 | 5500 | 24420
| Providing RCC M20 for footing( floor slab) | Cu.m | 14.4 | 4000 | 57600
| Providing and laying PCC 1:4:8 | Cu.m | 13.89 | 2650 | 36808.5
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 550 | 15 | 8250
Pump room and well works
| Providing and laying PCC 1:4:8 | Cu.m | 5.63 | 2650 | 14919.5
| Providing and constructing DR Masonary | Cu.m | 2.93 | 1500 | 4395
| Providing and constructing solid block walls | Cu.m | 6.73 | 5500 | 37015
| Prepare the surfaces and plaster in cm 1:4 | Sq.m | 97.08 | 325 | 31551
| Providing RCC M20 for Slabs | Cu.m | 2.75 | 10950 | 30112.5
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 390 | 15 | 5850
| Providing RCC M20 for Belts | Cu.m | 18.99 | 5000 | 94950
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 750 | 15 | 11250
M-Sand area Rt wall works
| Providing RCC M20 for footing | Cu.m | 56.36 | 4000 | 225440
| Providing RCC M20 for Walls | Cu.m | 68.5 | 10950 | 750075
| Providing RCC M20 for Columns | Cu.m | 5.09 | 10950 | 55735.5
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 8400 | 15 | 126000
Plant area works
| Providing RCC M20 for footing | Cu.m | 4.5 | 4000 | 18000
| Providing and constructing DR Masonary | Cu.m | 749.09 | 1500 | 1123635
| Providing RCC M20 for Belts | Cu.m | 76.02 | 5000 | 380100
| Providing RCC M20 for Columns | Cu.m | 25.17 | 10950 | 275611.5
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 9400 | 15 | 141000
Boundry KKJ
| Providing RCC M20 for footing | Cu.m | 40.83 | 4000 | 163320
| Providing RCC M20 for Walls | Cu.m | 27.53 | 10950 | 301453.5
| Providing RCC M20 for Columns | Cu.m | 3.18 | 10950 | 34821
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 4830 | 15 | 72450
Pond area
| Providing and laying PCC 1:4:8 | Cu.m | 4.45 | 2650 | 11792.5
New plant area works
| Providing RCC M20 for footing( floor slab) | Cu.m | 21.56 | 4000 | 86240
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 700 | 15 | 10500
| Providing and constructing solid block walls | Cu.m | 3.84 | 5500 | 21120
Soak pit 1 & 2
| Providing and constructing DR Masonary | Cu.m | 21.92 | 1500 | 32880
| Providing RCC M20 for Slabs | Cu.m | 1.64 | 10950 | 17958
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 75 | 15 | 1125
Sump tank works
| Providing RCC M20 for footing( floor slab) | Cu.m | 4.8 | 4000 | 19200
| Providing RCC M20 for Walls | Cu.m | 9.06 | 10950 | 99207
| Providing RCC M20 for Slabs | Cu.m | 1.46 | 10950 | 15987
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 2000 | 15 | 30000
| Prepare the surfaces and plaster in cm 1:4 | Sq.m | 42.6 | 325 | 13845
| Providing water proofing for all surfaces | Sq.m | 42.34 | 400 | 16936
Old plant area works
| Providing RCC M20 for Slabs | Cu.m | 1.14 | 10950 | 12483
| Cutting,bending and tying steel reinforcement for all RCC works | kg | 70 | 15 | 1050
| Additional labour wages |  |  |  | 523200
| Total |  |  |  | 6113190.25

## Crusher
Crusher work
S.No | Description | Nos | Length | Breadth | Depth | Qty | Remarks
Dam works
| Providing and laying PCC 1:4:8 | 1 | 31.5 | 2.8 | 0.15 | 13.23
[6 empty] | 13.23 | Cu.m
| Providing and laying RCC M20 Footing | 1 | 31.5 | 1.5 | 0.45 | 21.2625
|  | 1 | 31.5 | 1 | 0.3 | 9.45
|  | 1 | 3 | 1 | 0.75 | 2.25
[6 empty] | 32.9625 | Cu.m
| Providing and laying RCC M20 Wall | 1 | 31.5 | 0.4 | 5.3 | 66.78
|  | 1 | 2 | 0.4 | 1 | 0.8
|  | 1 | 3 | 0.4 | 3.76 | 4.512
|  | 1 | 3 | 0.35 | 3.15 | 3.3075
|  | 1 | 5.3 | 0.2 | 1.7 | 1.802
[6 empty] | 77.2015 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 17200 | kg
Drain works
| Providing and laying RCC M20 Footing | 1 | 3.6 | 1.2 | 0.22 | 0.9504
|  | 1 | 17.3 | 0.6 | 0.22 | 2.2836
|  | 1 | 9.8 | 1.75 | 0.47 | 8.0605
|  | 1 | 10.3 | 0.6 | 0.3 | 1.854
|  | 1 | 8.5 | 1.55 | 0.6 | 7.905
|  | 1 | 7.7 | 0.95 | 0.28 | 2.0482
|  | 1 | 11 | 0.6 | 0.25 | 1.65
|  | 1 | 7.5 | 0.55 | 0.3 | 1.2375
|  | 1 | 13.2 | 0.8 | 0.4 | 4.224
|  | 1 | 7 | 0.8 | 0.4 | 2.24
|  | 1 | 13 | 1.15 | 0.7 | 10.465
|  | 1 | 9 | 0.45 | 0.6 | 2.43
|  | 1 | 7.45 | 1.6 | 0.3 | 3.576
|  | 1 | 7 | 0.5 | 0.18 | 0.63
|  | 1 | 22 | 0.6 | 0.18 | 2.376
[6 empty] | 51.9302 | Cu.m
| Providing and laying RCC M20 Wall | 1 | 17.3 | 0.15 | 1.15 | 2.9842
|  | 1 | 9.8 | 0.15 | 1.15 | 1.6905
|  | 1 | 10.3 | 0.15 | 1.15 | 1.7768
|  | 1 | 8.5 | 0.15 | 1.15 | 1.4662
|  | 1 | 7.7 | 0.15 | 1.15 | 1.3282
|  | 1 | 11 | 0.15 | 1.15 | 1.8975
|  | 1 | 7.5 | 0.15 | 1.2 | 1.35
|  | 1 | 13.2 | 0.33 | 2.35 | 10.2366
|  | 1 | 7 | 0.33 | 1.87 | 4.3197
|  | 1 | 13 | 0.15 | 1.1 | 2.145
|  | 1 | 9 | 0.15 | 1.05 | 1.4175
|  | 1 | 7.45 | 0.15 | 1 | 1.1175
|  | 1 | 7 | 0.15 | 1.05 | 1.1025
|  | 1 | 22 | 0.15 | 0.95 | 3.135
[6 empty] | 35.9673 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 3700 | kg
Work shop
| Providing and laying PCC 1:4:8 | 1 | 3.47 | 1.3 | 0.3 | 1.3533
|  | 1 | 3.47 | 0.1 | 0.12 | 0.04164
|  | 1 | 2.68 | 0.15 | 0.2 | 0.0804
|  | 1 | 2.95 | 0.5 | 0.2 | 0.295
|  | 1 | 3 | 0.5 | 0.1 | 0.15
|  | 1 | 3.3 | 0.5 | 0.1 | 0.165
|  | 1 | 19 | 0.5 | 0.1 | 0.95
|  | 1 | 9 | 0.5 | 0.1 | 0.45
|  | 1 | 1.35 | 0.5 | 0.1 | 0.0675
|  | 4 | 4.1 | 0.5 | 0.1 | 0.82
|  | 1 | 4.8 | 3 | 0.1 | 1.44
[6 empty] | 5.8128 | Cu.m
| Providing and constructing Solid block walls | 1 | 1.06 | 0.7 | 0.6 | 0.4452
|  | 1 | 2.68 | 0.15 | 0.2 | 0.0804
|  | 1 | 1.1 | 0.15 | 0.4 | 0.066
|  | 1 | 4.2 | 0.15 | 1 | 0.63
|  | 1 | 1.8 | 0.15 | 0.6 | 0.162
|  | 1 | 1.45 | 0.15 | 0.68 | 0.1479
|  | 1 | 1 | 0.15 | 0.2 | 0.03
|  | 1 | 3.3 | 0.1 | 0.4 | 0.132
|  | 1 | 0.9 | 0.1 | 0.2 | 0.018
|  | 1 | 4.1 | 0.1 | 0.2 | 0.082
|  | 1 | 4.1 | 0.1 | 0.63 | 0.2583
|  | 1 | 4.1 | 0.1 | 0.63 | 0.2583
[6 empty] | 2.3101 | Cu.m
Canteen Area
| Providing and laying PCC 1:4:8 | 1 | 3 | 3 | 0.1 | 0.9 | Cu.m
| Providing and constructing Solid block walls | 1 | 4.6 | 0.1 | 2.6 | 1.196
|  | 1 | 0.9 | 0.1 | 0.6 | 0.054
[6 empty] | 1.25 | Cu.m
| Prepare the surfaces and plaster in cm 1:4 | 1 | 4.6 | 2.6 |  | 11.96
|  | 2 | 2.95 | 2.6 |  | 15.34
|  | 1 | 0.9 | 0.6 |  | 0.54
|  | 1 | 4.6 | 2.8 |  | 12.88
| less | 1 | 0.9 | 2.1 |  |  | 1.89
|  | 1 | 2.2 | 0.9 |  |  | 1.98
[6 empty] | 40.72 | 3.87
[6 empty] | 36.85 | sqm
Quarry Road area works
| Providing and laying PCC 1:4:8 ( Using Ajax mix) | 1 | 3 | 0.5 | 0.1 | 0.15
|  | 1 | 5.4 | 1.2 | 0.1 | 0.648
|  | 1 | 48 | 0.7 | 0.1 | 3.36
|  | 1 | 16 | 1.8 | 0.2 | 5.76
|  | 1 | 104 | 0.7 | 0.1 | 7.28
|  | 1 | 110 | 0.7 | 0.1 | 7.7
[6 empty] | 24.898 | Cu.m
Providing and constructing Solid block walls
| For flower trough | 1 | 3 | 0.1 | 0.4 | 0.12
|  | 1 | 2.9 | 0.1 | 0.4 | 0.116
|  | 1 | 20 | 0.1 | 0.2 | 0.4
|  | 1 | 3.2 | 0.1 | 0.4 | 0.128
|  | 1 | 3 | 0.1 | 0.4 | 0.12
|  | 1 | 3.05 | 0.1 | 0.4 | 0.122
|  | 1 | 3.06 | 0.1 | 0.4 | 0.1224
|  | 1 | 3.15 | 0.1 | 0.4 | 0.126
|  | 1 | 3 | 0.1 | 0.4 | 0.12
|  | 1 | 20 | 0.1 | 0.2 | 0.4
|  | 3 | 3.1 | 0.1 | 0.4 | 0.372
|  | 1 | 3.05 | 0.1 | 0.4 | 0.122
|  | 3 | 3.05 | 0.1 | 0.4 | 0.366
|  | 3 | 3.1 | 0.1 | 0.4 | 0.372
|  | 2 | 3.15 | 0.1 | 0.4 | 0.252
|  | 1 | 20 | 0.1 | 0.2 | 0.4
|  | 1 | 7.4 | 0.1 | 0.2 | 0.148
|  | 1 | 3.15 | 0.1 | 0.4 | 0.126
|  | 21 | 0.6 | 0.1 | 0.4 | 0.504
[6 empty] | 4.4364 | Cu.m
| Providing and laying RCC M 20 for floor slab | 1 | 8 | 9 | 0.2 | 14.4 | Cu.m
| Providing and laying PCC 1:4:8 for drain | 1 | 7.75 | 2.4 | 0.1 | 1.86
|  | 1 | 5 | 8.35 | 0.1 | 4.175
|  | 1 | 8.35 | 2.1 | 0.1 | 1.7535
|  | 1 | 21.45 | 1.6 | 0.1 | 3.432
| crass barrier support | 22 | 0.45 | 0.45 | 0.6 | 2.673
[6 empty] | 13.8935 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 550 | kg
Pump Room and Well works
| Providing and laying PCC 1:4:8 | 1 | 4.45 | 2.2 | 0.1 | 0.979
|  | 1 | 5.7 | 6.4 | 0.12 | 4.3776
|  | 1 | 3.75 | 0.6 | 0.12 | 0.27
[6 empty] | 5.6266 | Cu.m
| Providing and constructing Dry Rubble masonary | 1 | 2.64 | 0.5 | 0.4 | 0.528
|  | 1 | 2.5 | 0.4 | 0.3 | 0.3
|  | 3 | 3.5 | 0.5 | 0.4 | 2.1
[6 empty] | 2.928 | Cu.m
| Providing and constructing Solid block walls | 3 | 2.64 | 0.3 | 0.4 | 0.9504
|  | 1 | 2.5 | 0.3 | 0.2 | 0.15
|  | 2 | 4.13 | 0.3 | 0.4 | 0.9912
|  | 2 | 4.95 | 0.15 | 2.1 | 3.1185
|  | 3 | 2.2 | 0.15 | 2.1 | 2.079
| less | 2 | 0.88 | 0.15 | 2.1 |  | 0.5544
[6 empty] | 7.2891 | 0.5544
[6 empty] | 6.7347 | Cu.m
| Prepare the surfaces and plaster in cm 1:4 | 2 | 5.03 | 0.4 |  | 4.024
|  | 2 | 2.6 | 0.4 |  | 2.08
|  | 1 | 0.3 | 3.3 |  | 0.99
|  | 2 | 4.95 | 2.1 |  | 20.79
|  | 4 | 2.2 | 2.1 |  | 18.48
|  | 2 | 2.5 | 2.1 |  | 10.5
|  | 2 | 4.45 | 2.1 |  | 18.69
|  | 1 | 4.45 | 2.1 |  | 9.345
|  | 2 | 6.2 | 0.7 |  | 8.68
|  | 2 | 2.5 | 0.7 |  | 3.5
[6 empty] | 97.079 | sqm
| Providing and laying RCC M20 for slab | 1 | 6.2 | 3.7 | 0.12 | 2.7528 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 390 | kg
| Providing and laying RCC M20 for Belt | 1 | 4.2 | 1.2 | 0.2 | 1.008
|  | 1 | 4.4 | 1.2 | 0.2 | 1.056
|  | 2 | 7.32 | 1.2 | 0.2 | 3.5136
|  | 2 | 8 | 1.3 | 0.2 | 4.16
|  | 2 | 4.9 | 1.3 | 0.2 | 2.548
|  | 2 | 8 | 1.3 | 0.2 | 4.16
|  | 2 | 4.9 | 1.3 | 0.2 | 2.548
[6 empty] | 18.9936 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 750 | kg
M-Sand area Rt wall works
| Providing and laying RCC M20 Footing | 1 | 3 | 3 | 0.8 | 7.2
|  | 1 | 3.1 | 3 | 0.65 | 6.045
|  | 1 | 2.15 | 3 | 0.6 | 3.87
|  | 1 | 4.2 | 3 | 1.2 | 15.12
|  | 1 | 4.38 | 3 | 1 | 13.14
|  | 1 | 6.1 | 2 | 0.9 | 10.98
[6 empty] | 56.355 | Cu.m
| Providing and laying RCC M20 Wall | 1 | 0.5 | 0.3 | 3.17 | 0.4755
|  | 1 | 6.1 | 0.3 | 3.25 | 5.9475
|  | 1 | 2.4 | 0.45 | 4 | 4.32
|  | 1 | 3.1 | 0.45 | 4.77 | 6.6541
|  | 1 | 5.2 | 0.45 | 7 | 16.38
|  | 1 | 3.8 | 0.45 | 7 | 11.97
|  | 0.5 | 3 | 0.45 | 5.2 | 3.51
|  | 1 | 3.5 | 0.45 | 5.2 | 8.19
|  | 1 | 26 | 0.25 | 1.7 | 11.05
[6 empty] | 68.4972 | Cu.m
| Providing and laying RCC M20 for Columns | 8 | 0.5 | 0.2 | 1.75 | 1.4
|  | 3 | 0.6 | 0.15 | 7 | 1.89
|  | 2 | 0.6 | 0.15 | 6 | 1.08
|  | 2 | 0.6 | 0.15 | 4 | 0.72
[6 empty] | 5.09 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 8400 | kg
Plant Area works
| Providing and laying RCC M20 Footing | 1 | 7.5 | 1.5 | 0.4 | 4.5 | Cu.m
| Providing and constructing Dry Rubble masonary | 1 | 9.34 | 2.2 | 1.1 | 22.6028
|  | 1 | 6.1 | 2.2 | 0.7 | 9.394
|  | 1 | 28 | 2.2 | 1.2 | 73.92
|  | 1 | 10.8 | 2.2 | 1.85 | 43.956
|  | 1 | 7.1 | 2.2 | 1.3 | 20.306
|  | 1 | 3.9 | 2.2 | 0.6 | 5.148
|  | 1 | 2.5 | 2.2 | 0.95 | 5.225
|  | 1 | 13.3 | 2.1 | 1.2 | 33.516
|  | 1 | 60.8 | 2.35 | 1.65 | 235.752
|  | 1 | 60.5 | 2 | 1.8 | 217.8
|  | 1 | 25.5 | 1.4 | 2 | 71.4
|  | 1 | 1.9 | 0.7 | 0.45 | 0.5985
|  | 1 | 5.6 | 1.4 | 2.5 | 19.6
|  | 1 | 2 | 1 | 0.5 | 1
|  | 1 | 27 | 1.5 | 1.45 | 58.725
| less | 1 | 0.3 | 2.2 | 0.7 |  | 0.462
|  | 1 | 13.3 | 2.1 | 1.9 |  | 53.067
|  | 1 | 8.5 | 1.6 | 1.2 |  | 16.32
[6 empty] | 818.9433 | 69.849
[6 empty] | 749.09 | Cu.m
| Providing and laying RCC M20 for Belt | 1 | 15.45 | 2.2 | 0.15 | 5.0985
|  | 1 | 28 | 2.2 | 0.15 | 9.24
|  | 1 | 10.8 | 2.2 | 0.15 | 3.564
|  | 1 | 7.1 | 2.2 | 0.15 | 2.343
|  | 1 | 3.9 | 2.2 | 0.15 | 1.287
|  | 1 | 2.5 | 2.2 | 0.15 | 0.825
|  | 1 | 13.4 | 2.1 | 0.15 | 4.221
|  | 1 | 8.5 | 1.55 | 0.15 | 1.9763
|  | 1 | 60.8 | 2.2 | 0.15 | 20.064
|  | 1 | 60.5 | 1.8 | 0.15 | 16.335
|  | 1 | 25.5 | 1 | 0.15 | 3.825
|  | 1 | 1.9 | 0.7 | 0.15 | 0.1995
|  | 1 | 5.6 | 1.2 | 0.15 | 1.008
|  | 1 | 5.6 | 1 | 0.15 | 0.84
|  | 1 | 2.2 | 1 | 0.15 | 0.33
|  | 1 | 27 | 1.2 | 0.15 | 4.86
[6 empty] | 76.0162 | Cu.m
| Providing and laying RCC M20 for Columns | 14 | 0.6 | 0.6 | 1.65 | 8.316
|  | 14 | 0.6 | 0.6 | 1.85 | 9.324
|  | 2 | 0.4 | 0.6 | 1.75 | 0.84
|  | 5 | 0.4 | 0.6 | 2.65 | 3.18
|  | 3 | 0.4 | 0.6 | 1.75 | 1.26
|  | 4 | 0.6 | 0.6 | 1.25 | 1.8
|  | 1 | 0.6 | 0.6 | 0.95 | 0.342
|  | 1 | 0.6 | 0.6 | 0.6 | 0.216
|  | 2 | 0.6 | 0.6 | 1.2 | 0.864
|  | 2 | 0.6 | 0.6 | 1.8 | 1.296
|  | 2 | 0.6 | 0.6 | 2.5 | 1.8
|  | 2 | 0.6 | 0.6 | 0.8 | 0.576
|  | 2 | 0.6 | 0.6 | 1.4 | 1.008
|  | 2 | 0.6 | 0.6 | 1.2 | 0.864
| less | 2 | 0.6 | 0.6 | 1.9 |  | 1.368
|  | 2 | 0.65 | 0.65 | 1.1 |  | 0.9295
|  | 1 | 13.4 | 2.1 | 0.15 |  | 4.221
[6 empty] | 31.686 | 6.5185
[6 empty] | 25.17 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 9400 | kg
Boundry KKJ
| Providing and laying RCC M20 Footing | 1 | 2.57 | 2.4 | 0.5 | 3.084
|  | 1 | 2.4 | 2.4 | 0.52 | 2.9952
|  | 1 | 5.43 | 2.4 | 0.6 | 7.8192
|  | 1 | 7.4 | 2.4 | 0.72 | 12.7872
|  | 1 | 5.15 | 3 | 0.6 | 9.27
|  | 1 | 1.4 | 2.4 | 0.75 | 2.52
|  | 1 | 1.4 | 2.4 | 0.4 | 1.344
|  | 1 | 2.6 | 1.3 | 0.3 | 1.014
[6 empty] | 40.8336 | Cu.m
| Providing and laying RCC M20 Wall | 1 | 1.75 | 0.3 | 2.5 | 1.3125
|  | 1 | 2.3 | 0.3 | 2.94 | 2.0286
|  | 1 | 5.5 | 0.3 | 3.35 | 5.5275
|  | 1 | 7.3 | 0.3 | 3.45 | 7.5555
|  | 1 | 5.1 | 0.3 | 3.75 | 5.7375
|  | 1 | 1.3 | 0.3 | 2.95 | 1.1505
|  | 1 | 1.2 | 0.3 | 2.6 | 0.936
|  | 1 | 2.6 | 0.3 | 2.2 | 1.716
|  | 1 | 2.05 | 0.3 | 2.55 | 1.5682
[6 empty] | 27.5324 | Cu.m
| Providing and laying RCC M20 for Columns | 2 | 0.6 | 0.3 | 3.35 | 1.206
|  | 1 | 0.6 | 0.3 | 3.45 | 0.621
|  | 2 | 0.6 | 0.3 | 3.75 | 1.35
[6 empty] | 3.177 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 4830 | KG
Pond Area
| Providing and laying PCC 1:4:8 | 1 | 6.3 | 2 | 0.1 | 1.26
|  | 1 | 6 | 2 | 0.1 | 1.2
|  | 1 | 2.25 | 2 | 0.1 | 0.45
|  | 1 | 7.7 | 2 | 0.1 | 1.54
[6 empty] | 4.45 | Cu.m
New Plant area Works
| Providing and laying RCC M 20 for floor slab | 1 | 13.5 | 11.5 | 0.15 | 23.2875
| less | 1 | 3.4 | 3.4 | 0.15 |  | 1.734
[6 empty] | 21.56 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 700 | kg
| Providing and constructing Solid block flower trough | 2 | 0.6 | 0.1 | 0.4 | 0.048
|  | 2 | 47.4 | 0.1 | 0.4 | 3.792
[6 empty] | 3.84 | Cu.m
Soak pit works -1 & 2
| Providing and constructing Dry Rubble masonary | 2 | 3.8 | 0.6 | 1.35 | 6.156
|  | 2 | 1.75 | 0.6 | 1.35 | 2.835
|  | 1 | 5.5 | 0.6 | 1.2 | 3.96
| road side | 1 | 8.3 | 0.6 | 1.8 | 8.964
[6 empty] | 21.915 | Cu.m
| Providing and laying RCC M 20 for slab | 1 | 3.8 | 2.35 | 0.12 | 1.0716
|  | 1 | 0.8 | 0.8 | 0.12 | 0.0768
|  | 1 | 2.1 | 2.1 | 0.12 | 0.5292
| less | 1 | 0.6 | 0.6 | 0.12 |  | 0.0432
[6 empty] | 1.6776 | 0.0432
[6 empty] | 1.64 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 75 | kd
Sump Tank works
| Providing and laying RCC M 20 for floor slab | 1 | 4 | 4 | 0.3 | 4.8 | Cu.m
| Providing and laying RCC M20 Wall | 2 | 3.47 | 0.25 | 2.8 | 4.858
|  | 2 | 3 | 0.25 | 2.8 | 4.2
[6 empty] | 9.058 | Cu.m
| Providing and laying RCC M 20 for slab | 1 | 3.47 | 3.5 | 0.12 | 1.4574 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 2000 | kg
| Prepare the surfaces and plaster in cm 1:4 | 4 | 3 | 2.8 |  | 33.6
|  | 1 | 3 | 3 |  | 9
[6 empty] | 42.6 | Sq.m
| Providing water proofing for walls | 1 | 3 | 2.97 |  | 8.91
|  | 2 | 3 | 2.8 |  | 16.8
|  | 2 | 2.97 | 2.8 |  | 16.632
[6 empty] | 42.342 | Sq.m
Old Plant Area works
| Providing and laying RCC M 20 for slab | 1 | 4.3 | 1.4 | 0.15 | 0.903
| road side | 1 | 2.5 | 0.8 | 0.12 | 0.24
[6 empty] | 1.143 | Cu.m
| Cutting bending and tying steel reinforcement for all RCC Works |  |  |  |  | 70 | kg
Additional Labour charges
pond area
| helper | 6 | 800 |  |  | 4800
| labour shed | 12 | 800 |  |  | 9600
| mining area shed | 31 | 800 |  |  | 24800
| mining road | 20 | 800 |  |  | 16000
| sump tank area | 7 | 800 |  |  | 5600
| soak pit | 2 | 800 |  |  | 1600
| road works | 1 | 1200 |  |  | 1200
| vazithala road works | 7 | 800 |  |  | 5600
| m sand area toilet | 2 | 800 |  |  | 1600
| plant inside compacting | 4 | 800 |  |  | 3200
| GP 2 Plant | 4 | 900 |  |  | 3600
| road concreting quarry | 8 | 800 |  |  | 6400
| Hitachi Workshop | 10 | 800 |  |  | 8000
| toilet area block fixing | 1 | 1300 |  |  | 1300
|  | 1 | 1000 |  |  | 1000
| clay pipe support | 1 | 1000 |  |  | 1000
| toilet tiling | 2 | 1300 |  |  | 2600
|  | 2 | 1000 |  |  | 2000
| road cutting | 2 | 800 |  |  | 1600
| KKJ Compound wall | 28 | 800 |  |  | 22400
| m sand area | 18 | 800 |  |  | 14400
| rubble joint cley fixing | 33 | 800 |  |  | 26400
| cley removing | 12 | 800 |  |  | 9600
| earth filling planter boxes | 31 | 800 |  |  | 24800
| cement unloading | 10 | 1500 | non |  | 15000
| m sand area wall dismantling | 6 | 800 |  |  | 4800
| dam earth work | 10 | 800 |  |  | 8000
| drainage work | 33 | 800 |  |  | 26400
| anchering works | 19 | 950 |  |  | 18050
| gutter works | 50 | 1100 |  |  | 55000
| road side dr | 26 | 1100 |  |  | 28600
| interlock area concreting | 4 | 800 |  |  | 3200
| m sand area gutter works | 3 | 800 |  |  | 2400
| canteen area concreting | 4 | 800 |  |  | 3200
| parakadavu road | 20 | 1100 |  |  | 22000
|  | 10 | 900 |  |  | 9000
| compound wall top jally works | 10 | 900 |  |  | 9000
|  | 10 | 800 |  |  | 8000
| board fixing | 2 | 800 |  |  | 1600
| m sand levelling | 2 | 800 |  |  | 1600
| rain water gutter | 18 | 1100 |  |  | 19800
| rt wall earth work | 9 | 800 |  |  | 7200
| rt wall extention | 4 | 800 |  |  | 3200
| shed plastering | 15 | 1300 |  |  | 19500
|  | 10 | 1100 |  |  | 11000
| Total |  |  |  |  | 475650
| Add 10% oh & cp |  |  |  |  | 47565
| Total |  |  |  |  | 523215
Say Rs 5,23,200/-